## Product Backlog
Product Name:
Team ID:
Name: | Will Darden
Initials: | WD
Student ID: | 1001427242
(Additional names for teams only)
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 18
Sprint 1 Left | 18
Sprint 2 Left | 18
Sprint 3 Left | 18
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | As a... | I want to... | So that... | Notes
| 1 |  |  | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
| 2 |  |  | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
| 3 |  |  | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
| 4 |  |  | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
| 5 |  |  | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to disk and reload it next time the program runs
| 6 |  |  | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
| 7 |  |  | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
| 8 |  |  | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
| 9 |  |  | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
| 10 |  |  | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
| 11 |  |  | SA | create a bulk (2+) robot order for a Customer | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
| 12 |  |  | PM | hide robot parts | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models
| 13 |  |  | PM | hide robot models | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders
| 14 |  |  | SA | save a draft order and return to it later | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
| 15 |  |  | PM | add custom pictures to robot models | BC are more likely to buy my robots | (Probably can't address until Homework #6)
| 16 |  |  | BC | see a pie chart of a model's component costs | I can decide if I want a different model | (Probably can't address until Homework #6)
| 17 |  |  | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
| 18 |  |  | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)

## Sample
Sprint # |  |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on
Total Tasks | 23
Day 1 Left | 22
Day 2 Left | 19
Day 3 Left | 15
Day 4 Left | 15
Day 5 Left | 9
Day 6 Left | 4
Day 7 Left | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 01 Backlog
Sprint # | 1 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-07-31
End on | 2016-08-06
Demo on
Total Tasks | 30
Day 1 Left | 30
Day 2 Left | 29
Day 3 Left | 22
Day 4 Left | 22
Day 5 Left | 13
Day 6 Left | 12
Day 7 Left | 12
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | 0 |  |  | WD | Make Activity Diagram | Complete
2 | 0 |  |  | WD | Make class diagram | Complete
3 | 1 |  |  | WD | Write Part class | Complete
4 | 1 |  |  | WD | Write Part test | Complete
5 | 1 |  |  | WD | Write Head class | Complete
6 | 1 |  |  | WD | Write Arm class | Complete
7 | 1 |  |  | WD | Write Battery class | Complete
8 | 1 |  |  | WD | Write Battery test | Pending
9 | 1 |  |  | WD | Write Locomotor class | Complete
10 | 1 |  |  | WD | Write Locomotor test | Pending
11 | 1 |  |  | WD | Write Torso class | Complete
12 | 1 |  |  | WD | Write Torso test | Pending
13 | 1 |  |  | WD | Write Shop class | Complete
14 | 1 |  |  | WD | Write Shop test | Pending
15 | 1 |  |  | WD | Write Globals.h (Menu enum) | Complete
16 | 1 |  |  | WD | Write controller class | Complete
17 | 1 |  |  | WD | Write controller test | Pending
18 | 1 |  |  | WD | Write view class | Complete
19 | 1 |  |  | WD | Write view test | Pending
20 | 1 |  |  | WD | Write main class | Complete
21 | 2 |  |  | WD | Write Customer class | Complete
22 | 2 |  |  | WD | Write Customer test | Pending
23 | 2 |  |  | WD | Write Associate class | Complete
24 | 2 |  |  | WD | Write Associate test | Pending
25 | 2 |  |  | WD | Write Date enum header | Complete
26 | 2 |  |  | WD | Write Date test | Pending
27 | 2 |  |  | WD | Write Status enum header | Complete
28 | 2 |  |  | WD | Write status test | Pending
29 | 2 |  |  | WD | Write order class | Complete
30 | 2 |  |  | WD | Write order test | Pending
31 | 0 |  |  | WD | Create github repository | Complete
32 | 0 |  |  | WD | Upload all diagrams to computer | Pending